## Plan
Technology Focus Areas | Sl No | Tasks | Technologies involved | Resource | Backup Resource
Open Source Sensor Hub | 1.1 | Download and set up opensource sensor hub | Opensource Sensor Hub | Shivan/Sumeet | Shrini
| 1.11 | Setup eclipse and find appropriate maven pom file.
| 1.12 | Understand how to connect to devices/Simulators using different protocols
| 1.13 | Understand how we can club data from different sensors.
| 1.14 | Understand how this data can be pushed to a KAFKA message queue
Cassandra | 2.1 | Able to receive messages from OpenSourceSensorHub | Cassandra | Rohit Kumar | Rohit Mittal
| 2.11 | Set up Cassandra, understand basic concepts, partitions, Clusters, key space and tables.
| 2.12 | Store incoming messages in batch mode
| 2.13 | Able to query and show the data sets
| 2.14 | Write java Scripts to clean up and set up training data - may have to handle 100000 rows
Spark - Build time | 3.1 | Download Spark | Spark, Eclipse,Maven | Anjesh | Shrini
| 3.11 | Set up spark on Eclipse
| 3.12 | Run sample programs and understand the concepts
| 3.13 | Read training data from Cassandra
| 3.14 | Able to prepare the Machine learning model
Spark - Run time | 3.1 | Download Spark | Spark, Eclipse,Maven | Anjesh | Shrini
| 3.11 | Set up spark on Eclipse
| 3.12 | Run sample programs and understand the concepts
| 3.13 | Read training data from Cassandra
| 3.14 | Able to prepare the Machine learning model
Cassandra | 4.1 | Download Cassandra | Cassandra, Eclipse, Maven | Rohit Kumar | Rohit Mittal
| 4.11 | Set up Cassandra on Eclipse, identify Maven configuration
| 4.12 | Understand Cassandra concepts, Tables, Key spaces, Partitioning data, Clustering.
| 4.13 | Deep dive in to CRUD operations.
| 4.14 | Create a table to store incoming data.
| 4.15 | Integrate Kafka with Cassandra to publish messages on Kafka queue
| 4.16 | Read incomging data from Sensor Hub and store in Cassandra
| 4.17 | Batch update for incoming messages.
| 4.18 | Archive approaches.
| 4.19 | Partitioning and Clusterign the Cassandra Database
| 4.2 | CRUD operation using Spark jobs.
Kafka | 5.1 | Setup Kafka/Zookeeper | Kafka, Zookeeper, Eclipse, Maven | Mohit | Shrini
| 5.11 | Understand how to create topics
| 5.12 | Starting and stopping Kafka and Zookeeper
| 5.13 | Run sample code to send and receive messages on Kafka Queue
| 5.14 | Read messages from SensorHub from a Input queue
| 5.15 | Receive input messages from SensorHub
| 5.16 | Massage and refine the message
| 5.17 | Publish the message on the a Kafka ouput Queue
Kafka Spark integration | 6.1 | Receive Kafka message in Spark Job | Kafka, Spark, Eclipse,Maven | Anjesh/Shrini | Mohit
| 6.11 | Extract the data from the message
| 6.12 | Pass the message to Spark MLIB
| 6.13 | Publish the Alert on the Kafka output Queue
Spark Cassandra | 7.1 | Able to access the Cassandra table in Spark job | Spark, Cassandra, Eclipse,Maven | Rohit Kumar | Mohit
| 7.11 | Able to format the alert and input sensor reading in the JSON format
| 7.12 | Store the JSON in Cassandra table
| 7.13 | Publish to Kafka Queue
Ui/Middle ware | 8.1 | Node JS Web service to receive Kafka messages | Node JS/Web Socket/Rickshaw Chart | Neeraj | Help From Manoharan
| 8.11 | Socket IO integration with Node JS And Angular JS for pusbhing Alerts to UI
| 8.12 | Integration of Socket io with Rickshaw charts to show dynamic charts
Android Mobile | 9.1 | Basic UI to show alerts - Low priority | Android, Android Studio | Neeraj | Help From Manoharan

## Softwares
Software | Version
Operating System | Windows 10
Java | JDK 1.8
Spark | spark-1.6.3-bin-hadoop2.6
Cassandra | apache-cassandra-3.0.10
Kafka | kafka_2.10-0.10.0.0
Zookeeper | zookeeper-3.4.8
OpenSourceSensorHub | Latest Release
Maven | apache-maven-3.3.9
Node | node-v4.4.7-x64
HTML5
Angular JS | Angular 1.2